MPSR [Attribute(DomainPartition.Name)]

# Summary Header

Data Date: [Attribute(DataDate)]

Issuance Date: [Attribute(IssuanceDate)]

Overall Project Status: [Attribute(Path=OverallProjectStatus,VisibleWhen=Equals,Value=Low Risk,VisibleValue=Low Risk)][Attribute(Path=OverallProjectStatus,VisibleWhen=Equals,Value=Elevated Risk,VisibleValue=Elevated Risk)][Attribute(Path=OverallProjectStatus,VisibleWhen=Equals,Value=High Risk,VisibleValue=High Risk)]

SCHEDULE

Substantial Completion. Overall Schedule Status; Project Phase; Original Baseline Date; Revised (Approved) Baseline Date; Current Forecast/ Actual Date; Slippage from Baseline; Slippage from Previous Month; SPI. [Attribute(Path=OverallScheduleStatus,VisibleWhen=Equals,Value=Low Risk,VisibleValue=Low Risk)][Attribute(Path=OverallScheduleStatus,VisibleWhen=Equals,Value=Elevated Risk,VisibleValue=Elevated Risk)][Attribute(Path=OverallScheduleStatus,VisibleWhen=Equals,Value=High Risk,VisibleValue=High Risk)]; [Attribute(ProjectPhase)]; [Attribute(BaselineSCDate)]; [Attribute(RevisedSCDate)]; [Attribute(CurrentForecastSCDate)]; [Attribute(SCSlippagefromBaseline)]; [Attribute(SCSlippagefromPreviousMonth)]; [Number(Path=SPI,Format=”F2”)].

COST

Budget Performance; Percentages. Overall Budget Status; Revised (approved) Budget; Total VOW; Forecast (EAC); Variance at Completion; Percent Spent; Duration Percent Complete; Reported Physical Percent Complete. [Attribute(Path=OverallBudgetStatus,VisibleWhen=Equals,Value=Low Risk,VisibleValue=Low Risk)][Attribute(Path=OverallBudgetStatus,VisibleWhen=Equals,Value=Elevated Risk,VisibleValue=Elevated Risk)][Attribute(Path=OverallBudgetStatus,VisibleWhen=Equals,Value=High Risk,VisibleValue=High Risk)]; [Attribute(RevisedBudget)]; [Attribute(TotalVOW)]; [Number(Path=EstimateAtComplete, Format=”C0”)]; [Attribute(VarianceatCompletion)]; [Number(Path=PercentSpent,Format=”F1”)]%; [Number(Path=DurationPercentComplete,Format=”F1”)]%; [Number(Path=ReportedPhysicalPercentComplete,Format=”F1”)]%.

RISK

Contingency Budget; Risk Exposure; Schedule Risk Analysis (QSRA). Original Contingency; Projected Remaining; Percent Consumed; Required Contingency (Risk Exposure); Gap between Required & Projected Remaining Contingency; QSRA; Slippage From Baseline. [Attribute(OriginalContingency)]; [Attribute(ProjectedRemaining)]; [Number(Path=PercentConsumed,Format=”F2”)]; [Attribute(RequiredContingencyRiskExposure)]; [Attribute(GapbetweenRequiredProjectedRemainingContingency)]; [Attribute(QSRA)]; [Attribute(SlippagefromBaseline)].

| QUALITY |  | SAFETY |
| --- | --- | --- |
| Non Conformances; Injury Statistics. Open NCRs; Closed NCRs; Exposure Hours; Total Critical Injuries or Fatalities. [Attribute(OpenNCRs)]; [Attribute(ClosedNCRs)]; [Attribute(ExposureHours)]; [Attribute(TotalCriticalInjuriesorFatalities)]. |

# General Project Information

Project Number; Scope Summary; Sector. [Attribute(ProjectNumber)]; [Attribute(ScopeSummary)]; [Attribute(Sector)]. Project Name; Client Name; Project Type. [Attribute(ProjectName)]; [Attribute(ClientName)]; [Attribute(ProjectType)]. Pco/Contractor; Project Stage; PC Level of Service. [Attribute(PcoContractor.ShortLabel)]; [Attribute(ProjectStage)]; [Attribute(PCLevelofService)]. Prime Consultant Name (PDC/TA/AOR); Contract; Property Number & Name. [Attribute(PrimeConsultantName.ShortLabel)]; [Attribute(Contract)]; [Attribute(BuildingNumberName)]. External PM; Key Quantity; Key Quantity UOM; Land Number & Name. [Attribute(ExternalPM.ShortLabel)]; [Attribute(KeyQuantity)]; [Attribute(KeyQuantityUOM)]; [Attribute(LandNumberName)]. Project Address; Key Quantity 2; Key Quantity 2 UOM; Building Number & Name. [Attribute(ProjectAddress)]; [Attribute(KeyQuantity2)]; [Attribute(KeyQuantity2UOM)]; [Attribute(PropertyNumberName)].

Key Stakeholders

[StartTable(Name=KeyStakeholders,Source=Attribute,Path=KeyStakeholders,RowsInHeader=2)]

| Details |  |  |
| --- | --- | --- |
| Organization | Role Name | Person |
| [Attribute(Organization)] | [Attribute(RoleName)] | [Attribute(Person)] |

[EndTable]

| Is Final MPSR? | [Attribute(IsFinalMPSR)] |
| --- | --- |

# Schedule

Milestones

[StartTable(Name=Milestones,Source=Attribute,Path=Milestones,Sort=MilestoneNumber Ascending,RowsInHeader=2)]

| Details |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity ID | Milestone Name | Original Baseline Finish Date | Revised Baseline Finish Date | Forecast Finish Date | Actual Finish Date | Slippage From Revised | Slippage From Previous Period | Commentary |
| [Attribute(MilestoneNumber)] | [Attribute(MilestoneName)] | [Attribute(OriginalBaselineFinishDate)] | [Attribute(RevisedBaselineFinishDate)] | [Attribute(ForecastFinishDate)] | [Attribute(ActualFinishDate)] | [Attribute(SlippageFromRevised)] | [Attribute(SlippageFromPreviousPeriod)] | [Attribute(Commentary)] |

[EndTable]

Schedule Comments

[Attribute(ScheduleComments)]

Site Progress Narrative

[Attribute(SiteProgressNarrative)]

# Cost

@[<StartTable Name=”CostOverview” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”Parent.Id” TotalMode=”Summary”>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”LatestApprovedBudget” TargetPath=”SumLatestApprovedBudget” />
        <Path SourcePath=”BudgetRevised” TargetPath=”SumBudgetRevised” />
        <Path SourcePath=”BudgetRevisedFromPreviousPeriod” TargetPath=”SumBudgetRevisedFromPreviousPeriod” />
        <Path SourcePath=”BudgetPeriodApprovedChanges” TargetPath=”SumBudgetPeriodApprovedChanges” />
        <Path SourcePath=”CommitmentsRevised” TargetPath=”SumCommitmentsRevised” />
        <Path SourcePath=”CommitmentsRevisedFromPreviousPeriod” TargetPath=”SumCommitmentsRevisedFromPreviousPeriod” />
        <Path SourcePath=”CommitmentsPeriodApprovedChanges” TargetPath=”SumCommitmentsPeriodApprovedChanges” />
        <Path SourcePath=”IncurredCostVOWD” TargetPath=”SumIncurredCostVOWD” />
        <Path SourcePath=”IncurredCostVOWDfromPreviousPeriod” TargetPath=”SumIncurredCostVOWDfromPreviousPeriod” />
        <Path SourcePath=”PeriodIncurredCostVOWD” TargetPath=”SumPeriodIncurredCostVOWD” />
        <Path SourcePath=”EAC” TargetPath=”SumEAC” />
        <Path SourcePath=”EACfromPreviousPeriod” TargetPath=”SumEACfromPreviousPeriod” />
        <Path SourcePath=”PeriodEAC” TargetPath=”SumPeriodEAC” />
        <Path SourcePath=”VarianceatCompletion” TargetPath=”SumVarianceatCompletion” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”CostOverview” />
    <AnyOf>
     <Data Path=”LatestApprovedBudget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”BudgetRevised” Type=”NotEqualTo” Value=”0” />
     <Data Path=”BudgetRevisedFromPreviousPeriod” Type=”NotEqualTo” Value=”0” />
     <Data Path=”CommitmentsRevised” Type=”NotEqualTo” Value=”0” />
     <Data Path=”CommitmentsRevisedFromPreviousPeriod” Type=”NotEqualTo” Value=”0” />
     <Data Path=”CommitmentsPeriodApprovedChanges” Type=”NotEqualTo” Value=”0” />
     <Data Path=”IncurredCostVOWD” Type=”NotEqualTo” Value=”0” />
     <Data Path=”IncurredCostVOWDfromPreviousPeriod” Type=”NotEqualTo” Value=”0” />
     <Data Path=”PeriodIncurredCostVOWD” Type=”NotEqualTo” Value=”0” />
     <Data Path=”PeriodPercentSpent” Type=”NotEqualTo” Value=”0” />
     <Data Path=”EAC” Type=”NotEqualTo” Value=”0” />
     <Data Path=”EACfromPreviousPeriod” Type=”NotEqualTo” Value=”0” />
     <Data Path=”PeriodEAC” Type=”NotEqualTo” Value=”0” />
     <Data Path=”VarianceatCompletion” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Cost Overview |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost Breakdown Structure |  | Budget |  |  |  | Commitments |  |  | Incurred Cost |  |  |  |  | Estimate-at-Completion |  |  |  |
| CBS Code | CBS Name | Baseline | Budget Revised | Budget Revised from Previous Period | Budget Period Approved Changes | Commitments Revised | Commitments Revised From Previous Period | Commitments Period Approved Changes | Incurred Cost (VOW) | Incurred Cost (VOW) from Previous Period | Period Incurred Cost (VOW) | Percent Spent | Period Percent Spent | EAC | EAC from Previous Period | Period EAC | Variance at Completion |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(LatestApprovedBudget)] | [Attribute(BudgetRevised)] | [Attribute(BudgetRevisedFromPreviousPeriod)] | [Attribute(BudgetPeriodApprovedChanges)] | [Attribute(CommitmentsRevised)] | [Attribute(CommitmentsRevisedFromPreviousPeriod)] | [Attribute(CommitmentsPeriodApprovedChanges)] | [Attribute(IncurredCostVOWD)] | [Attribute(IncurredCostVOWDfromPreviousPeriod)] | [Attribute(PeriodIncurredCostVOWD)] | [Number(Path=PercentSpent,Format=”F1”)]% | [Number(Path=PeriodPercentSpent,Format=”F1”)]% | [Attribute(EAC)] | [Attribute(EACfromPreviousPeriod)] | [Attribute(PeriodEAC)] | [Attribute(VarianceatCompletion)] |
| [TableGroupTotalRow] | [Attribute(ItemType)] Total | [Currency(Path=SumLatestApprovedBudget)] | [Currency(Path=SumBudgetRevised)] | [Currency(Path=SumBudgetRevisedFromPreviousPeriod)] | [Currency(Path=SumBudgetPeriodApprovedChanges)] | [Currency(Path=SumCommitmentsRevised)] | [Currency(Path=SumCommitmentsRevisedFromPreviousPeriod)] | [Currency(Path=SumCommitmentsPeriodApprovedChanges)] | [Currency(Path=SumIncurredCostVOWD)] | [Currency(Path=SumIncurredCostVOWDfromPreviousPeriod)] | [Currency(Path=SumPeriodIncurredCostVOWD)] |  |  | [Currency(Path=SumEAC)] | [Currency(Path=SumEACfromPreviousPeriod)] | [Currency(Path=SumPeriodEAC)] | [Currency(Path=SumVarianceatCompletion)] |

@[<EndTable/>]

@[<StartTable Name=”TimephasedCosts” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”Parent.Id” TotalMode=”Summary”>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”BudgetRevised” TargetPath=”SumBudgetRevised” />
        <Path SourcePath=”EAC” TargetPath=”SumEAC” />
        <Path SourcePath=”IncurredCostVOWD” TargetPath=”SumIncurredCostVOWD” />
        <Path SourcePath=”PriorYearsIncurred” TargetPath=”SumPriorYearsIncurred” />
        <Path SourcePath=”IncurredCostVOWDThisYear” TargetPath=”SumIncurredCostVOWDThisYear” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”CostOverview” />
    <AnyOf>
     <Data Path=”BudgetRevised” Type=”NotEqualTo” Value=”0” />
     <Data Path=”EAC” Type=”NotEqualTo” Value=”0” />
     <Data Path=”IncurredCostVOWD” Type=”NotEqualTo” Value=”0” />
     <Data Path=”PriorYearsIncurred” Type=”NotEqualTo” Value=”0” />
     <Data Path=”IncurredCostVOWDThisYear” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Timephased Costs |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Cost Breakdown Structure |  | Budget |  | Incurred Cost |  |  |
| CBS Code | CBS Name | Budget Revised | Forecast | Value of Work | Prior Years Incurred | Current Year’s Incurred Cost (VOW) |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(BudgetRevised)] | [Attribute(EAC)] | [Attribute(IncurredCostVOWD)] | [Attribute(PriorYearsIncurred)] | [Attribute(IncurredCostVOWDThisYear)] |
| [TableTotalRow] | Total | [Currency(Path=SumBudgetRevised)] | [Currency(Path=SumEAC)] | [Currency(Path=SumIncurredCostVOWD)] | [Currency(Path=SumPriorYearsIncurred)] | [Currency(Path=SumIncurredCostVOWDThisYear)] |

@[<EndTable/>]

@[<StartTable Name=”TimephasedCosts2” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”2”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”Parent.Id” TotalMode=”Summary”>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”ThisYearQ1Incurred” TargetPath=”SumThisYearQ1Incurred” />
        <Path SourcePath=”ThisYearQ1Budget” TargetPath=”SumThisYearQ1Budget” />
        <Path SourcePath=”ThisYearQ1Forecast” TargetPath=”SumThisYearQ1Forecast” />
        <Path SourcePath=”ThisYearQ2Incurred” TargetPath=”SumThisYearQ2Incurred” />
        <Path SourcePath=”ThisYearQ2Budget” TargetPath=”SumThisYearQ2Budget” />
        <Path SourcePath=”ThisYearQ2Forecast” TargetPath=”SumThisYearQ2Forecast” />
        <Path SourcePath=”ThisYearQ3Incurred” TargetPath=”SumThisYearQ3Incurred” />
        <Path SourcePath=”ThisYearQ3Budget” TargetPath=”SumThisYearQ3Budget” />
        <Path SourcePath=”ThisYearQ3Forecast” TargetPath=”SumThisYearQ3Forecast” />
        <Path SourcePath=”ThisYearQ4Incurred” TargetPath=”SumThisYearQ4Incurred” />
        <Path SourcePath=”ThisYearQ4Budget” TargetPath=”SumThisYearQ4Budget” />
        <Path SourcePath=”ThisYearQ4Forecast” TargetPath=”SumThisYearQ4Forecast” />
        <Path SourcePath=”ThisYearTotalIncurred” TargetPath=”SumThisYearTotalIncurred” />
        <Path SourcePath=”ThisYearTotalBudget” TargetPath=”SumThisYearTotalBudget” />
        <Path SourcePath=”ThisYearTotalForecast” TargetPath=”SumThisYearTotalForecast” />
        <Path SourcePath=”ForecastVariance” TargetPath=”SumForecastVariance” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”CostOverview” />
    <AnyOf>
     <Data Path=”ThisYearQ1Incurred” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ1Budget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ1Forecast” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ2Incurred” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ2Budget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ2Forecast” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ3Incurred” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ3Budget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ3Forecast” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ4Incurred” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ4Budget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearQ4Forecast” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearTotalIncurred” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearTotalBudget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ThisYearTotalForecast” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ForecastVariance” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Cost Breakdown Structure |  | Timephased Costs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CBS Code | CBS Name | Q1 Incurred | Q1 Budget | Q1 Forecast | Q2 Incurred | Q2 Budget | Q2 Forecast | Q3 Incurred | Q3 Budget | Q3 Forecast | Q4 Incurred | Q4 Budget | Q4 Forecast | This Year Total Incurred | This Year Total Budget | This Year Total Forecast | Forecast Variance |  |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(ThisYearQ1Incurred)] | [Attribute(ThisYearQ1Budget)] | [Attribute(ThisYearQ1Forecast)] | [Attribute(ThisYearQ2Incurred)] | [Attribute(ThisYearQ2Budget)] | [Attribute(ThisYearQ2Forecast)] | [Attribute(ThisYearQ3Incurred)] | [Attribute(ThisYearQ3Budget)] | [Attribute(ThisYearQ3Forecast)] | [Attribute(ThisYearQ4Incurred)] | [Attribute(ThisYearQ4Budget)] | [Attribute(ThisYearQ4Forecast)] | [Attribute(ThisYearTotalIncurred)] | [Attribute(ThisYearTotalBudget)] | [Attribute(ThisYearTotalForecast)] |  | [Attribute(ForecastVariance)] |
| [TableTotalRow] | Total | [Currency(Path=SumThisYearQ1Incurred)] | [Currency(Path=SumThisYearQ1Budget)] | [Currency(Path=SumThisYearQ1Forecast)] | [Currency(Path=SumThisYearQ2Incurred)] | [Currency(Path=SumThisYearQ2Budget)] | [Currency(Path=SumThisYearQ2Forecast)] | [Currency(Path=SumThisYearQ3Incurred)] | [Currency(Path=SumThisYearQ3Budget)] | [Currency(Path=SumThisYearQ3Forecast)] | [Currency(Path=SumThisYearQ4Incurred)] | [Currency(Path=SumThisYearQ4Budget)] | [Currency(Path=SumThisYearQ4Forecast)] | [Currency(Path=SumThisYearTotalIncurred)] | [Currency(Path=SumThisYearTotalBudget)] | [Currency(Path=SumThisYearTotalForecast)] |  | [Currency(Path=SumForecastVariance)] |

@[<EndTable/>]

@[<StartTable Name=”TimephasedCosts3” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”2”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”Parent.Id” TotalMode=”Summary”>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”NextYearBudget” TargetPath=”SumNextYearBudget” />
        <Path SourcePath=”NextYearForecast” TargetPath=”SumNextYearForecast” />
        <Path SourcePath=”SubsequentYearsBudget” TargetPath=”SumSubsequentYearsBudget” />
        <Path SourcePath=”SubsequentYearsForecast” TargetPath=”SumSubsequentYearsForecast” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”CostOverview” />
    <AnyOf>
     <Data Path=”NextYearBudget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”NextYearForecast” Type=”NotEqualTo” Value=”0” />
     <Data Path=”SubsequentYearsBudget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”SubsequentYearsForecast” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Cost Breakdown Structure |  | Forecast |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CBS Code | CBS Name | Next Year Budget | Next Year Forecast | Subsequent Years Budget | Subsequent Years Forecast |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(NextYearBudget)] | [Attribute(NextYearForecast)] | [Attribute(SubsequentYearsBudget)] | [Attribute(SubsequentYearsForecast)] |
| [TableTotalRow] | Total | [Currency(Path=SumNextYearBudget)] | [Currency(Path=SumNextYearForecast)] | [Currency(Path=SumSubsequentYearsBudget)] | [Currency(Path=SumSubsequentYearsForecast)] |

@[<EndTable/>]

Invoicing Status

| Previous Year(s) |  | Current Year |  | Total |  |
| --- | --- | --- | --- | --- | --- |
| VOW | Invoices Approved for Payment | VOW | Invoices Approved for Payment | VOW | Invoices Approved for Payment |
| [Attribute(PreviousYearVOW)] | [Attribute(PreviousYearInvoicesApprovedforPayment)] | [Attribute(CurrentYearVOW)] | [Attribute(CurrentYearInvoicesApprovedforPayment)] | [Attribute(TotalVOW)] | [Attribute(TotalInvoicesApprovedforPayment)] |
| Previous Month |  | Current Month |  |  |  |
| VOW | Invoices Approved for Payment | VOW | Invoices Approved for Payment |  |  |
| [Attribute(PreviousMonthVOW)] | [Attribute(PreviousMonthInvoicesApprovedforPayment)] | [Attribute(CurrentMonthVOW)] | [Attribute(CurrentMonthInvoicesApprovedforPayment)] |  |  |

@[<StartTable Name=”ContingencyStatus” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”Parent.Id” TotalMode=”Summary”>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”InitialContingencyBaselineBudget” TargetPath=”SumInitialContingencyBaselineBudget” />
        <Path SourcePath=”ContingencyApprovedChanges” TargetPath=”SumContingencyApprovedChanges” />
        <Path SourcePath=”RemainingContingency” TargetPath=”SumRemainingContingency” />
        <Path SourcePath=”ContingencyPendingChanges” TargetPath=”SumContingencyPendingChanges” />
        <Path SourcePath=”ContingencyPotentialChanges” TargetPath=”SumContingencyPotentialChanges” />
       <Path SourcePath=”ProjectedRemainingContingencyProjectedBudget” TargetPath=”SumProjectedRemainingContingencyProjectedBudget” />
       <Path SourcePath=”PercentContingencyRemaining” TargetPath=”SumPercentContingencyRemaining” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”Contingency” />
    <AnyOf>
     <Data Path=”InitialContingencyBaselineBudget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ContingencyApprovedChanges” Type=”NotEqualTo” Value=”0” />
     <Data Path=”RemainingContingency” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ContingencyPendingChanges” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ContingencyPotentialChanges” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ProjectedRemainingContingencyProjectedBudget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”PercentContingencyRemaining” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Contingency Status |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost Breakdown Structure |  | Contingency Budget |  |  |  |  |  |  |
| CBS Code | CBS Name | Initial Contingency (Baseline Budget) | Contingency Approved Changes | Remaining Contingency | Contingency Pending Changes | Contingency Potential Changes | Projected Remaining Contingency (Projected Budget) | Percent Contingency Remaining |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(InitialContingencyBaselineBudget)] | [Attribute(ContingencyApprovedChanges)] | [Attribute(RemainingContingency)] | [Attribute(ContingencyPendingChanges)] | [Attribute(ContingencyPotentialChanges)] | [Attribute(ProjectedRemainingContingencyProjectedBudget)] | [Number(Path=PercentContingencyRemaining,Format=”P”)] |
| [TableTotalRow] | Total | [Currency(Path=SumInitialContingencyBaselineBudget)] | [Currency(Path=SumContingencyApprovedChanges)] | [Currency(Path=SumRemainingContingency)] | [Currency(Path=SumContingencyPendingChanges)] | [Currency(Path=SumContingencyPotentialChanges)] | [Currency(Path=SumProjectedRemainingContingencyProjectedBudget)] |  |

@[<EndTable/>]

@[<StartTable Name=”ContingencyStatus2” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”2”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”Parent.Id” TotalMode=”Summary”>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”AdditionalCostRiskExposure” TargetPath=”SumAdditionalCostRiskExposure” />
        <Path SourcePath=”RequiredContingencyEAC” TargetPath=”SumRequiredContingencyEAC” />
       <Path SourcePath=”RequiredContingencyfromPreviousPeriod” TargetPath=”SumRequiredContingencyfromPreviousPeriod” />
       <Path SourcePath=”PeriodRequiredContingencyChange” TargetPath=”SumPeriodRequiredContingencyChange” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”Contingency” />
    <AnyOf>
     <Data Path=”AdditionalCostRiskExposure” Type=”NotEqualTo” Value=”0” />
     <Data Path=”RequiredContingencyEAC” Type=”NotEqualTo” Value=”0” />
     <Data Path=”RequiredContingencyfromPreviousPeriod” Type=”NotEqualTo” Value=”0” />
     <Data Path=”PeriodRequiredContingencyChange” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Cost Breakdown Structure |  | Required Contingency |  |  |  |
| --- | --- | --- | --- | --- | --- |
| CBS Code | CBS Name | Additional Cost/ Risk Exposure | Required Contingency (EAC) | Required Contingency from Previous Period | Period Required Contingency Change |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(AdditionalCostRiskExposure)] | [Attribute(RequiredContingencyEAC)] | [Attribute(RequiredContingencyfromPreviousPeriod)] | [Attribute(PeriodRequiredContingencyChange)] |
| [TableTotalRow] | Total | [Currency(Path=SumAdditionalCostRiskExposure)] | [Currency(Path=SumRequiredContingencyEAC)] | [Currency(Path=SumRequiredContingencyfromPreviousPeriod)] | [Currency(Path=SumPeriodRequiredContingencyChange)] |

@[<EndTable/>]

@[<StartTable Name=”CashAllowanceStatus” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”Parent.Id” TotalMode=”Summary”>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”LatestApprovedBudget” TargetPath=”SumLatestApprovedBudget” />
        <Path SourcePath=”ApprovedBudgetChanges” TargetPath=”SumApprovedBudgetChanges” />
        <Path SourcePath=”BudgetRevised” TargetPath=”SumBudgetRevised” />
        <Path SourcePath=”IncurredCostVOWD” TargetPath=”SumIncurredCostVOWD” />
        <Path SourcePath=”ETC” TargetPath=”SumETC” />
       <Path SourcePath=”EAC” TargetPath=”SumEAC” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”CashAllowance” />
    <AnyOf>
     <Data Path=”LatestApprovedBudget” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ApprovedBudgetChanges” Type=”NotEqualTo” Value=”0” />
     <Data Path=”BudgetRevised” Type=”NotEqualTo” Value=”0” />
     <Data Path=”IncurredCostVOWD” Type=”NotEqualTo” Value=”0” />
     <Data Path=”PercentSpent” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ETC” Type=”NotEqualTo” Value=”0” />
     <Data Path=”EAC” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Cash Allowance Status |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost Breakdown Structure |  | Cash Allowance Budget |  |  | Incurred Cost |  | Cash Allowance Forecast |  |
| CBS Code | CBS Name | Baseline | Approved Changes | Budget Revised | Incurred Cost (VOW) | Percent Spent | ETC | EAC |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(LatestApprovedBudget)] | [Attribute(ApprovedBudgetChanges)] | [Attribute(BudgetRevised)] | [Attribute(IncurredCostVOWD)] | [Attribute(PercentSpent,Format=”F1”)]% | [Attribute(ETC)] | [Attribute(EAC)] |
| [TableTotalRow] | Total | [Currency(Path=SumLatestApprovedBudget)] | [Currency(Path=SumApprovedBudgetChanges)] | [Currency(Path=SumBudgetRevised)] | [Currency(Path=SumIncurredCostVOWD)] |  | [Currency(Path=SumETC)] | [Currency(Path=SumEAC)] |

@[<EndTable/>]

@[<StartTable Name=”BudgetDevelopmentHistory” Source=”Attribute” Path=”CBSColumns” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”CBSCode.Code” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Where>
   <AllOf>
    <Data Path=”RecordType” Type=”EqualTo” Value=”CostOverview” />
    <AnyOf>
     <Data Path=”HistoricalBudget1” Type=”NotEqualTo” Value=”0” />
     <Data Path=”HistoricalBudget2” Type=”NotEqualTo” Value=”0” />
     <Data Path=”HistoricalBudget3” Type=”NotEqualTo” Value=”0” />
     <Data Path=”HistoricalBudget4” Type=”NotEqualTo” Value=”0” />
     <Data Path=”LatestApprovedBudget” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
   </AllOf>
  </StartTable.Where>
</StartTable>]

| Budget Development History |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Cost Breakdown Structure |  | Historical Budgets |  |  |  | Budget |
| CBS Code | CBS Name | Historical Budget 1 | Historical Budget 2 | Historical Budget 3 | Historical Budget 4 | Baseline |
| [Attribute(CBSCode.Code)] | [Attribute(CBSName)] | [Attribute(HistoricalBudget1)] | [Attribute(HistoricalBudget2)] | [Attribute(HistoricalBudget3)] | [Attribute(HistoricalBudget4)] | [Attribute(LatestApprovedBudget)] |

@[<EndTable/>]

@[<StartTable Name=”BudgetChangeSummary” Source=”Attribute” Path=”BudgetChangeSummary” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”ChangeCategoryType” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Where>
   <AnyOf>
    <Data Path="IgnoreInPV" Type="EqualTo" Value="No" />
    <Data Path="IgnoreInPV" Type="HasNoValue" />
   </AnyOf>
  </StartTable.Where>
</StartTable>]

| Budget Change Summary |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Change Category | Approved |  |  |  | Pending |  |
| Change Category Type | This Period Count | This Period Value | To Date Count | To Date Value | To Date Count | To Date Value |
| [Attribute(ChangeCategoryType)] | [Attribute(ApprovedThisPeriodCount)] | [Attribute(ApprovedThisPeriodValue)] | [Attribute(ApprovedToDateCount)] | [Attribute(ApprovedToDateValue)] | [Attribute(PendingToDateCount)] | [Attribute(PendingToDateValue)] |

@[<EndTable/>]

Budget Status Narrative

[Attribute(BudgetStatusNarrative)]

@[<StartTable Name=”Commitments” Source=”Attribute” Path=”Commitments” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”POContract” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Where>
    <AnyOf>
     <Data Path=”OriginalContractValue” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ApprovedChanges” Type=”NotEqualTo” Value=”0” />
     <Data Path=”RevisedContract” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ProjectedChanges” Type=”NotEqualTo” Value=”0” />
     <Data Path=”ProjectedCommitments” Type=”NotEqualTo” Value=”0” />
    </AnyOf>
  </StartTable.Where>
</StartTable>]

| Commitments |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Details |  |  |  |  |  |  |  |
| PO/Contract # | Vendor ID | Vendor Name | Original Contract Value | Approved Changes | Revised Contract | Projected Commitment Changes | Projected Commitments |
| [Attribute(POContract)] | [Attribute(VendorID.ShortLabel)] | [Attribute(VendorName)] | [Attribute(OriginalContractValue)] | [Attribute(ApprovedChanges)] | [Attribute(RevisedContract)] | [Attribute(ProjectedChanges)] | [Attribute(ProjectedCommitments)] |

@[<EndTable/>]

@[<StartTable Name=”CommitmentChangeSummary” Source=”Attribute” Path=”CommitmentChangeSummary” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”ChangeCategoryType” Direction=”Ascending” />
  </StartTable.Sorts>
  <StartTable.Grouping GroupMode=”SubTotal” GroupBy=”ChangeCategory” TotalMode=”Summary”>>
   <Grouping.Operations>
    <Sum>
      <Sum.Paths>
        <Path SourcePath=”ApprovedThisPeriodCount” TargetPath=”SumApprovedThisPeriodCount” />
        <Path SourcePath=”ApprovedThisPeriodValue” TargetPath=”SumApprovedThisPeriodValue” />
        <Path SourcePath=”ApprovedToDateCount” TargetPath=”SumApprovedToDateCount” />
        <Path SourcePath=”ApprovedToDateValue” TargetPath=”SumApprovedToDateValue” />
        <Path SourcePath=”PendingToDateCount” TargetPath=”SumPendingToDateCount” />
        <Path SourcePath=”PendingToDateValue” TargetPath=”SumPendingToDateValue” />
      </Sum.Paths>
    </Sum>
   </Grouping.Operations>
  </StartTable.Grouping>
  <StartTable.Where>
    <AnyOf>
     <Data Path="IgnoreInPV" Type="EqualTo" Value="No" />
     <Data Path="IgnoreInPV" Type="HasNoValue" />
    </AnyOf>
  </StartTable.Where>
</StartTable>]

| Commitment Change Summary |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Change Category |  | Approved |  |  |  | Pending |  |
|  | Change Category Type | This Period Count | This Period Value | To Date Count | To Date Value | To Date Count | To Date Value |
| [TableGroupTotalRow] Total For | [Attribute(ChangeCategory)] | [Currency(Path=SumApprovedThisPeriodCount)] | [Currency(Path=SumApprovedThisPeriodValue)] | [Currency(Path=SumApprovedToDateCount)] | [Currency(Path=SumApprovedToDateValue)] | [Currency(Path=SumPendingToDateCount)] | [Currency(Path=SumPendingToDateValue)] |
|  | [Attribute(ChangeCategoryType)] | [Attribute(ApprovedThisPeriodCount)] | [Attribute(ApprovedThisPeriodValue)] | [Attribute(ApprovedToDateCount)] | [Attribute(ApprovedToDateValue)] | [Attribute(PendingToDateCount)] | [Attribute(PendingToDateValue)] |

@[<EndTable/>]

@[<StartTable Name=”ChangeDetails” Source=”Attribute” Path=”ChangeDetails” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”Number” Direction=”Ascending” />
  </StartTable.Sorts>
</StartTable>]

| Change Details |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Details |  |  |  |  |  |  |  |  |  |  |
| Change ID | Type | Related Issue | Vendor Name | Title | Status | Value | Receipt Date | Ball in Court | Change Category | Notes |
| [Attribute(Number)] | [Attribute(Type)] | [Attribute(RelatedIssue)] | [Attribute(VendorName)] | [Attribute(Title)] | [Attribute(Status)] | [Attribute(Value)] | [Attribute(ReceiptDate)] | [Attribute(BallinCourt)] | [Attribute(ChangeCategory)] | [Attribute(Notes)] |

@[<EndTable/>]

@[<StartTable Name=”ClaimsSummary” Source=”Attribute” Path=”ClaimStages” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”Number” Direction=”Ascending” />
  </StartTable.Sorts>
</StartTable>]

| Claim Summary |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Details |  |  | Total |  | This Period |  |
| Number | Subject | Count |  | Value | Count | Value |
| [Attribute(Number)] | [Attribute(Subject)] | [Number(Path=CountTotal,Format=”F0”)] |  | [Attribute(ValueTotal)] | [Number(Path=CountThisPeriod,Format=”F0”)] | [Attribute(ValueThisPeriod)] |

@[<EndTable/>]

@[<StartTable Name=”UnresolvedClaimDetails” Source=”Attribute” Path=”UnresolvedClaimDetails” RowsInHeader=”3”>
  <StartTable.Sorts>
    <Sort Path=”ClaimID.ShortLabel” Direction=”Ascending” />
  </StartTable.Sorts>
</StartTable>]

| Unresolved Claim Details |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Details |  |  |  |  |  |  |
| Claim ID | Vendor Name | Title | Status | Claim Stage | Value | Receipt Date |
| [Attribute(ClaimID.ShortLabel)] | [Attribute(VendorName)] | [Attribute(Title)] | [Attribute(Status)] | [Attribute(ClaimStage)] | [Attribute(Value)] | [Attribute(ReceiptDate)] |

@[<EndTable/>]

| Claims Status | [Attribute(ClaimsStatus)] |
| --- | --- |

# Risk

Risks

[StartTable(Name=Risks,Source=Attribute,Path=Risks,RowsInHeader=2)]

| Details |  |  | Pre-Mitigation |  |  | Post-Mitigation |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| ID | Category | Risk Title | Pre-Mitigation Level | Pre-Mitigation Trend | Mitigation Plan | Post-Mitigation Level | Post-Mitigation Trend |
| [Attribute(RiskID.ShortLabel)] | [Attribute(Category)] | [Attribute(RiskTitle)] | [Attribute(PreMitigationLevel)] | [Attribute(PreMitigationTrend)] | [Attribute(MitigationPlan)] | [Attribute(PostMitigationLevel)] | [Attribute(PostMitigationTrend)] |

[EndTable]

Issues

[StartTable(Name=Issues,Source=Attribute,Path=Issues,RowsInHeader=2)]

| Details |  |  |  |  |
| --- | --- | --- | --- | --- |
| ID | Description | Type | Status | Impact Amount |
| [Attribute(IssueID.ShortLabel)] | [Attribute(Description)] | [Attribute(Type)] | [Attribute(Status)] | [Attribute(ImpactAmount)] |

[EndTable]

Risk Status Narrative

[Attribute(RiskStatusNarrative)]

| # Project Management |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Count of RFIs |  |  | Summary of Submittals |  |  |
| Total | [Attribute(TotalRFIs)] |  |  | This Period | To Date |
| Open | [Attribute(OpenRFIs)] |  | Received | [Attribute(ThisPeriodReceivedSubmittals)] | [Attribute(ToDateReceivedSubmittals)] |
| # Open >15 Days | [Attribute(Open15DaysRFIs)] |  | Approved | [Attribute(ThisPeriodApprovedSubmittals)] | [Attribute(ToDateApprovedSubmittals)] |
| Closed | [Attribute(ClosedRFIs)] |  | Rejected | [Attribute(ThisPeriodRejectedSubmittals)] | [Attribute(ToDateRejectedSubmittals)] |
| Avg Turnaround | [Attribute(AvgTurnaroundRFIs)] |  |  |  |  |

Critical Outstanding Actions

[StartTable(Name=CriticalOutstandingActions,Source=Attribute,Path=CriticalOutstandingActions,RowsInHeader=2)]

| Details |  |  |  |
| --- | --- | --- | --- |
| Action Description | Owner | Due Date | Notes |
| [Attribute(ActionDescription)] | [Attribute(Owner.ShortLabel)] | [Attribute(DueDate)] | [Attribute(Notes)] |

[EndTable]

Overall Project Management

[Attribute(OverallProjectManagement)]

Contractor RFx Status

[Attribute(ContractorRFxStatus)]

Co-Sponsor Funding Commentary

[Attribute(CoSponsorFundingCommentary)]

IT FFE Planning

[Attribute(ITFFEPlanning)]

Due Diligence Commentary

[Attribute(DueDiligenceCommentary)]

Enabling Work Commentary

[Attribute(EnablingWorkCommentary)]

# Governance

Stage Gate Summary

[StartTable(Name=StageGateSummary,Source=Attribute,Path=StageGateSummary,RowsInHeader=2)]

| Details |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Gate | Status | Outstanding Checklist Items | # of Deviations | Completion Date | Approver |
| [Attribute(Gate)] | [Attribute(Status)] | [Attribute(OutstandingChecklistItems)] | [Attribute(NumofDeviations)] | [Attribute(CompletionDate)] | [Attribute(Approver)] |

[EndTable]

Due Diligence Checklist Details

[StartTable(Name=DueDiligenceChecklistDetails,Source=Attribute,Path=DueDiligenceChecklistDetails,RowsInHeader=2)]

| Details |  |  |  |  |
| --- | --- | --- | --- | --- |
| Gate | Checklist Item | Status | Approved Deviation? | Notes |
| [Attribute(Gate)] | [Attribute(ChecklistItem)] | [Attribute(Status)] | [Attribute(ApprovedDeviation)] | [Attribute(Notes)] |

[EndTable]

| # Quality |  |
| --- | --- |
| NCR Summary |  |  |
| Open NCRs | [Attribute(OpenNCRs)] |  |
| Closed NCRs | [Attribute(ClosedNCRs)] |  |
| Total NCRs | [Attribute(TotalNCRs)] |  |

Quality Narrative

[Attribute(QualityNarrative)]

| # Safety Summary |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Safety Summary |  |  |  |  |
| Exposure Hours | [Attribute(ExposureHours)] |  | Total Critical Injuries or Fatalities | [Attribute(TotalCriticalInjuriesorFatalities)] |
|  |  |  | Total Incidents Resulting in Lost Time LTI | [Attribute(TotalIncidentsResultinginLostTimeLTI)] |
|  |  |  | Total Incidents With No Lost Time | [Attribute(TotalIncidentsWithNoLostTime)] |
|  |  |  | Total Injuries to Any Member of the Public | [Attribute(TotalInjuriestoAnyMemberofthePublic)] |
|  |  |  | Total Incidents Involving Medical Aid or Healthcare | [Attribute(TotalIncidentsInvolvingMedicalAidorHealthcare)] |
|  |  |  | Total Incidents Involving First Aid | [Attribute(TotalIncidentsInvolvingFirstAid)] |
|  |  |  | Total Near Misses | [Attribute(TotalNearMisses)] |

Safety Status Narrative

[Attribute(SafetyStatusNarrative)]

# Other

Other Commentary

[Attribute(OtherCommentary)]