CONSTRUCTION OBSERVATIONS PERFORMED BY: Nelson Yang and Dielle Abamonga of Yogi Kwong Engineers, LLC (YKE): SITE ACTIVITIES: (06:30 – 15:00 hrs)

Site 1: Digester and SST Building

- HR continued to work at the Digesters

- HP continued to work at the Digesters

- DNT continued to work at the Digesters

- WASA continued to work at the Digesters

Site 2: EFW Reuse Pump Station (RPS)

- HP continued to work at RPS

Site 3: Primary Clarifier OCS Electrical Building (PCOCS)

- No work observed

Site 4: General Site

- HP continued to work at the General Site

- DNT continued to work at the General Site

DOWN TIME: No

WORK TYPE: Contract Work, Exhibit G

UPDATE(S) TO RECORD DWG: No

WEATHER: Mostly Cloudy 11 MPH, ENE

CONTRACTOR(S) ON-SITE: Hensel Phelps Construction Company (HPCC); WASA Electric (WASA); DN Tanks (DNT); Harris Rebar (HR), HC&D (HC&D), Hayre, McElroy and Associates, LLC (HMA), KAI Hawaii (KH).

SUMMARY OF ACTIVITIES:

Site 1: Digester and SST Building

- HR continued to work at the Digesters

  - HR continued to install #7 alternating J-hooks at the outer ring of Digester #4 approx. GL DIG4.A-DIG4.C, DIG4.1-DIG4.3

  - HR continued to install #7 T2 top mat rebars at the south of DCB approx GL DC.3-DIG4.1, DIG4.A-DC.C

  - HR continued to install #6 vertical dowels for the 1’-4” outer wall at the east and west DCB and Digester #4 approx GL DCB.E1-DCB.F, DC.2-DIG4.2

  - HR continued to install #9 vertical rebars and #4 Type T3 rebar hoops for the (3) C1 columns at the south of DCB approx GL DC.3, DC.A-DC.C

    - Refer to Synagro Submittal 0004-03210-4 DIG 3, DIG 4, DCB Foundation Rebar SD

- HP continued to work at the Digesters

  - HP continued to install trench drain formwork at the south of DCB approx GL DC.A-DC.C, DIG4.1-DIG4.2

    - Refer to Synagro Submittal 0001-05513-1 - Trench Drain Angle SD R1

- DNT continued to work at the Digesters

  - Concrete placement for Digester #3 section 1 skirt wall.

    - 96 CY of 5000 psi ¾” MR7SRA/WP concrete from HC&D was delivered.  HC&D provided delivery service.

    - 1st truck arrived at approximately 08:09 hours and slump test was taken by HMA technician. Slump test at 9-inches and temperature at 84 degrees Fahrenheit.  Jake Wheeles from DN Tanks suggested having the concrete truck stay idle and retake the slump test.  Third party inspector from Kai Hawaii and Rick Brook from Hensel Phelps concurred.

    - HMA technician retook the slump test in approximately 10 minutes, and the slump test was at 9 inches.

    - Jake Wheeles consulted with his design team and was given the approval to place the concrete.

    - Slump tests and concrete cylinder samples were taken for the first truck and second truck.  Second truck slump test at 7-3.4 inch and temperature at 86 degrees Fahrenheit.

    - DNT placed concrete through the window openings from 4 levels.  Each level openings fabricated to meet the maximum free fall height requirement.  (2) vibrators were used to consolidate the concrete.

    - DNT placed concrete from 08:00 to 14:00 hours.  96 CY of concrete was delivered and DNT discarded approximately 7 CY from the last truck.  Estimated concrete placed at 89 CY

  - DNT continued to install 1st and 2nd layer of rebar curtains for the Digester #3 section 2 skirt wall.

- WASA continued to work at the Digesters

  - WASA began to install JB housings and conduit connection to stubouts at the Digester #3 section 2 skirt wall area.

    - Refer to Synagro Submittal 0006-16000-0 DIG #4 Foundation and Skirt Wall Electrical Rough-in SD

Site 2: EFW Reuse Pump Station (RPS)

- HP continued to work at RPS

  - Exhibit G: Start-up for the #1 EFW pump and #1 strainer ongoing at RPS, plant personnel were on site to observe the activity, and the pressure gauge was at 49 psi.  Dielle Abamonga (YKE) was onsite to observe and document activity.

    - Refer to Pckg 2 Dwg No. C007, Pckg 1 Dwg No. M040

Site 3: Primary Clarifier OCS Electrical Building (PCOCS)

- No work observed

Site 4: General Site

- HP continued to work at the General Site.

- HP used the crane to relocate their equipment shelter.

NOTES / OBSERVATIONS / ATTACHMENTS:

- Synagro Submittal 0004-03210-4 DIG 3, DIG 4, DCB Foundation Rebar SD

- Synagro Submittal 0001-05513-1 - Trench Drain Angle SD R1

- Pckg 2 Dwg No. S611

- Synagro Submittal 0006-16000-0 DIG #4 Foundation and Skirt Wall Electrical Rough-in SD

- Synagro Submittal 0017-03210-0 Digester 3 Skirt Wall Reinforcing SD (FIO)

- Pckg 2 Dwg No. C007

- Pckg 1 Dwg No. M040

- Pckg 1 Dwg No. C2

- Concrete Tags Digester #3 Section 1 Skirt Wall  09/05/25

- Photo Contact Sheet

NOTICE

This Field Report was prepared by Yogi Kwong Engineers, LLC (YKE) and/or its subconsultants, under YKE’s Construction Management Contract with, and for the exclusive use by, the City and County of Honolulu (the City).  No one except the City may rely on or use information or statements contained in this Field Report.  Inferences made by others based on anything included in, or omitted from, this Field Report are their responsibility. Personnel employed by Yogi Kwong Engineers, LLC (YKE), and/or its subconsultants, were on site solely to observe, gather and document information for the City, related to the work being performed under the City’s construction contract with Hensel Phelps Construction Company (HPCC).   Per HPCC’s contract with the City, HPCC is solely responsible for safety and site security, construction means, methods, techniques, sequences, procedures, corrective measures, and all procedures employed by HPCC and its subcontractors in the performance of its contract with the City.